## Tabelle1
Tasks | Start Date | Duration | End Date
Decide on a programming language | 2019-10-24 | 1 | 2019-10-25
Research into general ethics | 2019-10-24 | 7 | 2019-10-31
Develop a basic action plan | 2019-10-24 | 14 | 2019-11-07
Establish concept design requirements | 2019-10-25 | 1 | 2019-10-26
Conceptual designs(First Person) | 2019-10-25 | 13 | 2019-11-07
Conceptual designs(Third person) | 2019-10-25 | 13 | 2019-11-07
Establish base of functionality | 2019-10-25 | 13 | 2019-11-07
Design a basic decision tree | 2019-10-25 | 13 | 2019-11-07
Produce a gantt chart | 2019-10-31 | 6 | 2019-11-06
Begin work on scenarios | 2019-10-31 | 14 | 2019-11-14
Create concept poster | 2019-10-31 | 21 | 2019-11-21
Research poster styles/themes | 2019-10-31 | 14 | 2019-11-14
Create first draft of poster | 2019-10-31 | 81 | 2020-01-20
Decide conditions for scenarios | 2019-10-31 | 1 | 2019-11-01
Begin studying JS | 2019-10-31
Create graphics for people in scenarios | 2019-11-07
Create graphics for environment | 2019-11-07
Create car graphics | 2019-11-07